## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | 1.1 | Jdk installation 21+. | Must Have | None |  | Done
| Sprint 1 | 1.2 | Crate JAVA project with meaningful name and mvn integration (mvn clean install). | Must Have | 1.1 |  | Done
Sprint 2 | Sprint 2 | 2.1 | Installed MySQL Server and created the bankdb database. | Must Have | 1.2 |  | Done
| Sprint 2 | 2.2 | Added the mysql-connector-java dependency to the pom.xml file. | Must Have | 1.2 |  | Done
| Sprint 2 | 2.3 | Created an application.properties file under src/main/resources folder and stored database credentials. | Must Have | 2.1, 2.2 |  | Done
| Sprint 2 | 2.4 | Implemented a DBConfig class to load properties and manage database connections. | Must Have | 2.3 |  | Done
Sprint 3 | Sprint 3 | 3.1 | Create POJO data models for Customer, Account, and Transaction. | Must Have | 2.4 |  | Done
| Sprint 3 | 3.2 | Implemented a DBSetup utility class to create the database schema (customers, accounts, transactions SCHEMA). | Must Have | 3.1 |  | Done
Sprint 4 | Sprint 4 | 4.1 | Created CustomerRepository and CustomerRepositoryImpl with full CRUD operations for the Customer entity using PreparedStatement. | Must Have | 3.2 |  | Done
| Sprint 4 | 4.2 | Added a handleSQLException helper to manage SQL exceptions and re-throw them as RuntimeException. | Should Have | 4.1 |  | Done
| Sprint 4 | 4.3 | Tested the CustomerRepositoryImpl CURD operations with hardcoded values. | Must Have | 4.1, 4.2 |  | Done
Sprint 5 | Sprint 5 | 5.1 | Install and configure Apache Tomcat 10, and change the Maven project packaging from JAR to WAR. | Must Have | 4.3 |  | Done
| Sprint 5 | 5.2 | Add and configure Jakarta Jersey dependencies (servlet, hk2, jackson, servlet-api) to the pom.xml. | Must Have | 5.1 |  | Done
| Sprint 5 | 5.3 | As a developer, I need to understand the difference between Catalina Home and Catalina Base and configure them correctly in IntelliJ for Tomcat deployment. | Could Have | 5.1 |  | Done
Sprint 6 | Sprint 6 | 6.1 | Implement Customer module APIs (POST /customer, GET /customer/{id}, GET /customer, PUT /customer/{id}, DELETE /customer/{id}) and update getCustomerById and deleteCustomer endpoints to accept customerId via JSON request body. | Must Have | 5.2 |  | Done
| Sprint 6 | 6.2 | Add validation for name (letters and spaces), phone number (10 digits, starts 6–9), and Aadhar (12 digits, starts 2–9) in CustomerServiceImpl. | Must Have | 6.1 |  | Done
| Sprint 6 | 6.3 | Configure Jackson to handle LocalDate serialization/deserialization for dob. | Should Have | 6.1 |  | Done
| Sprint 6 | 6.4 | Refactor service/repository to throw custom exceptions and use a global exception handler in CustomerController. | Must Have | 6.2 |  | Done
| Sprint 6 | 6.5 | Add JUnit 5 and Mockito, write unit tests for controller and service, and use DTOs (CustomerResponse) for API responses. | Should Have | 6.1–6.4 |  | Done
Sprint 7 | Sprint 7 | 7.1 | Add ifscCode to Account and define validation rules for accountNumber, ifscCode, balance, and enums. | Must Have | 6.1 |  | Done
| Sprint 7 | 7.2 | Refactor repository and service to use accountNumber for find, update, and delete. | Must Have | 7.1 |  | Done
| Sprint 7 | 7.3 | Implement AccountServiceImpl with business logic for open, close, deposit, withdraw, getAccountDetails, and checkBalance using MySQL defaults. | Must Have | 7.2 |  | Done
| Sprint 7 | 7.4 | Create custom exceptions (AccountNotFoundException, DuplicateAccountException, InsufficientBalanceException) and update service to throw them. | Should Have | 7.3 |  | Done
| Sprint 7 | 7.5 | Implement AccountController REST endpoints, refactor deposit/withdraw to use DTO/Map, and add deleteAccount. | Must Have | 7.3, 7.4 |  | Done
| Sprint 7 | 7.6 | Register GlobalExceptionHandler in JerseyConfig and test all APIs with error scenarios. | Should Have | 7.5 |  | Done
Sprint 8 | Sprint 8 | 8.1 | Implement TransactionServiceImpl with JDBC transaction management and transfer validations. | Must Have | 7.5 |  | Done
| Sprint 8 | 8.2 | Create TransactionController with POST /transaction/transfer accepting JSON input. | Must Have | 8.1 |  | Done
| Sprint 8 | 8.3 | Implement TransactionRepositoryImpl to save transactions via PreparedStatement. | Must Have | 8.1 |  | Done
| Sprint 8 | 8.4 | Write unit tests for service and controller, covering success and error cases. | Should Have | 8.2, 8.3 |  | Done
| Sprint 8 | 8.5 | Add Jakarta Mail, create EmailService for Gmail SMTP, and send notifications after transfers. | Could Have | 8.2 |  | Done
| Sprint 8 | 8.6 | Validate sender in TransactionServiceImpl using isCustomerValid() and throw CustomerNotFoundException | Must Have | 8.1 |  | Done
| Sprint 8 | 8.7 | Switch EmailService to Mailtrap and configure credentials in application.properties. | Could Have | 8.5 |  | Done
Sprint 9 | Sprint 9 | 9.1 | implement an API endpoint to export transaction history as a CSV file. | Should Have | 8.3 |  | Done
| Sprint 9 | 9.2 | Design and develop the Login page using React and Tailwind CSS with authentication logic in authApi.js to handle form data, POST login requests, manage session/token storage, and display error messages for invalid credentials | Must Have | 6.1, 7.5 |  | Done
| Sprint 9 | 9.3 | Implement session management and logout functionality to clear stored tokens and redirect users to the Login page. | Must Have | 9.2 |  | Done
Sprint 10 | Sprint 10 | 10.1 | Developed dynamic forms for creating new accounts and performing transactions, along with interactive cards to display individual account, customer, and transaction details, and list views for managing multiple records. | Must Have | 7.5, 8.2 |  | Done
| Sprint 10 | 10.2 | Implemented role-based pages for both Admin and User, ensuring access restrictions and dedicated interfaces, including HomePage, AccountPage, CustomerPage, and TransactionPage. | Must Have | 9.2 |  | Done
| Sprint 10 | 10.3 | Enhanced the Customer entity by adding password and role fields to support secure login functionality and role-based access control. | Must Have | 6.1, 9.2 |  | Done
| Sprint 10 | 10.4 | Developed and integrated API endpoints to establish seamless communication between the frontend and backend, ensuring reliable performance and smooth data exchange. | Must Have | 7.5, 8.2, 9.2 |  | Done
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7